## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | APPLIED AI PROJECT ¦ IT3389 |  |  |  |  | INSTITUTE | [6 empty] | NANYANG POLYTECHNIC
PROJECT TEAM |  | SIEW WEI HENG, ETHAN LEE, LIM GAVIN |  |  |  |  | START DATE | [6 empty] | 2024-12-10
[26 empty] | Preparation for Final Presentation | [9 empty] | Aftermath
WBS NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | Preparation for Milestone Report | [19 empty] | Preparation for Final Presentation | [9 empty] | Aftermath
[6 empty] | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 | [6 empty] | WEEK 17 |  |  | WEEK 18 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Preparation for Milestone Report (WEEK 14)
1.1 | Iterate of Project feedback | 2025-01-14 | 2025-01-15 | 1 | 100% | bar: WEEK 14 T to WEEK 14 W; WEEK 19 F
1.1.1 | Individual Additional Scraping to increase data collected | 2025-01-15 | 2025-01-17 | 2 | 100% | bar: WEEK 14 W to WEEK 14 F; WEEK 19 F
1.2 | Individual EDA | 2025-01-15 | 2025-01-17 | 2 | 90% | bar: WEEK 14 W to WEEK 14 F; WEEK 19 F
1.3 | Individual Testing of Models | 2025-01-15 | 2025-01-17 | 2 | 40% | bar: WEEK 14 W to WEEK 14 F; WEEK 19 F
1.4 | Deployment of Models onto Python server | 2025-01-17 | 2025-01-20 | 3 | 70% | bar: WEEK 14 F to WEEK 15 M; WEEK 19 F
1.5 | Prototyping of Web application | 2025-01-20 | 2025-01-31 | 11 | 60% | bar: WEEK 15 M to WEEK 16 F; WEEK 19 F
1.5 | Creation of Milestone Report | 2025-01-29 | 2025-02-03 | 4 | 60% | bar: WEEK 16 W to WEEK 16 M; WEEK 19 F
1.6 | Milestone Report submission | 2025-02-04 | 2025-02-04 | 0 | 0% | bar: WEEK 16 T; WEEK 19 F
2 | Preparation for Final Presentation (WEEK 17)
2.1 | Individual Web App (Done) | 2025-02-05 | 2025-02-11 | 6 | 0% | bar: WEEK 17 W to WEEK 18 T; WEEK 19 F
2.2 | Additional Model Optimisations | 2025-02-05 | 2025-02-11 | 6 | 0% | bar: WEEK 17 W to WEEK 18 T; WEEK 19 F
2.3 | Web App Integration (All) | 2025-02-12 | 2025-02-17 | 5 | 0% | bar: WEEK 18 W to WEEK 19 M; WEEK 19 F
2.4 | Final Presentation Slides | 2025-02-13 | 2025-02-17 | 4 | 0% | bar: WEEK 18 R to WEEK 19 M; WEEK 19 F
2.5 | Final Presentation | 2025-02-18 | 2025-02-18 | 0 | 0% | bar: WEEK 19 T; WEEK 19 F
3 | Aftermath of Final Presentation (WEEK 19)
3.1 | Adjustments to Final Presentation Report | 2025-02-19 | 2025-02-23 | 4 | 0% | bar: WEEK 19 W to WEEK 19 F
3.2 | Peer evaulation | 2025-02-19 | 2025-02-23 | 4 | 0% | bar: WEEK 19 W to WEEK 19 F
3.2.1 | Project end | 2025-02-23 | 2025-02-23 | 0 | 0% | bar: WEEK 19 F

## Sheet2
web app
Wei heng: | 14 | 15 | 16 | 17 | 18 | 19
Scraping | yes
EDA | yes
Test model | yes
Scraping part 2 | yes
EDA part 2 |  | yes
Train model |  | yes | yes
Deploy |  |  | yes | yes
Web app Dev |  |  | yes | yes
Web app Dev part 2 |  |  |  |  | yes
[5 empty] | yes | yes
yes